## Slide 1: OM, Services, Finance, & SC incl. Boundary Apps (Scenario 1)
Key accomplishment
Validated Scenario 1 with other validation sessions and partly offline
Next Steps | Owner | ECD
Updated Architecture based on feedback | BA Team | 4/6
RAID | Owner | ECD | Status
(#2442) Created 3/11: ABM CRP (3/1) : Scenario 1 and 5 Supply Chain Deep Dive Understand process for regulatory check for shipments | Rohit Chavan | 4/20/18 | Open
(#2618) Created 3/23: Unknow CRP Business need to understand the ABM model in relationship to Pricing strategy. Several process components are unknown and this reflects onto the associated ABM - pricing reporting. | Manish Mathur | 3/30/18 | Open
(#2552) Created 3/23: Unknown CRP​ ABM Translator from old to new structure and new to old structure needs to be available to support transition period. Need high level key design: | Mukul Agrawal | 4/10/18 | Open
(#2573) Created 3/26: Unknown CRP​ ​We are getting conflicting information in the CRP's regarding quote in S4 and the process flow is unclear. | Guillermo Vazquez | 3/30/18 | Open
RAID Snapshot:
April 6, 2018

## Slide 2: OM, Services, Finance, & SC incl. Boundary Apps (Scenario 2)
Key accomplishment
Conducted ABM Scenario 2 Validation of Fixed Price / Fixed Scope with Attach HW / SW / Services​
Process steps for Scenario 2 were covered highlighting Fixed Price/Fixed Scope Consulting Process with Project System
The following data objects were discussed with relation to Scenario 2: H/W, S/W, Services, Attributes and SKUs, Project, Planning, Budgeting​
Session completed for Hardware, Software, Reactive, Software with Package Consulting Service – periodic billing from a Boundary Applications standpoint
Continued to gather preliminary potential change topics for Scenario 2 including boundary applications
Next Steps | Owner | ECD
Transient Architecture view to be updated based on feedback provided prior to Align CRP on 4/10 | GA team | 
Detailed PS WBS structure discussion with the core team along with deep dive to define Project types, WBS levels, different fields and values required/optional to be updated in project/WBS definition | BA team | 
Understanding the business rules for cost and revenue planning​ |  | 
Covering derivation on profit centers and Cost objects in WBS Profiles |  | 
RAID | Owner | ECD | Status
(#2821) A) Make a note when we make deal management, approvals in S/4 and approvals in SFDC B) Line between S/4 and SFDC -> (SFDC to feed approval pricing information to S/4 for an eclipse like deal) RAID : Approval process would be in SFDC. Need to fully document approval process in slide. C) Work through the pluses and minuses of the quote in S/4 | David, Dwight |  | Open
(#2824) Create Sales order - Scenario 2 Step 8. If factory is not in S/4 then need to check in fusion. If factory is not in S/4 then FUSION Boundary app needs to be interfaced. -> This is covered under the order fulfillment bridge. But there is a gap with regard to ATP. | Lyfareff, Bob |  | Open
2826) Scenario 2 Create Sales Order RAID : CLIC is for legacy from Fusions for validations. Explain validation Assumption that we do CLIC validation for S/4 for the products coming in as a process for creating sales order. RAID : CLIC functionality needs to be determined around create sales order | David, Dwight |  | Open
2827) Create Sales order Scenario 2 ​ Big Rock: How SKUs will be loaded into S/4. Scott Moyer escalated to Hitesh. How do we take a list of SKUs from a quote and turn that into a configuration. How will it work in Day 1. | Tewari, Hitesh |  | Open
2828) Add step for Warranty reserve. S4 -> Interface to Armor (202179). This performs the warranty reserve. Where ever there is a warranty (Step 102). Warranty is HW related. (Ranganathan Sourirajan). Create a step for warranty reserve for S4 <-> Armor. Where ever there is HW, Armor should be present. | Tewari, Hitesh |  | Open
2829) Scenario 2 Project Close Project Generator -> S/4, Project Generator -> FF. Go-forward application. Urvish to confirm the role of project generator for steps 105, 106. | Desai, Urvish |  | Open
RAID Snapshot:
April 6, 2018

## Slide 3: OM, Services, Finance, & SC incl. Boundary Apps (Scenario 3)
Key accomplishment
There was considerable discussion on the accuracy of the steps, thus prolonging the conversation and preventing the validation from completing
Completed validation of 116 steps of 208
Next Steps | Owner | ECD
HPE has requested that the process steps be updated and a second validation session be scheduled | ABM team | 
Work with CRP team to revise process steps | BA team | 
Update architecture views based on revised process steps | BA team | 
RAID | Owner | ECD | Status
(#2896) ​Order capture bridge requirement deep dive needed to understand if it is used with Corona in context for Scenario 3 - Create Sales Order. | Malhotra, Meenakshi | 4/9/2018 | Open
(#2897) ​Step is missing for track and trace of shipment. Step missing Updating shipment record to get proof of delivery. Step 23 - should be shipment document created that gets updated | Davuluri, Neil | 4/9/2018 | Open
(#2899) ​Review scenario 3 and 5 for accuracy and if all the apps are included. | Lozano, Rosa A | 4/6/2018 | Open
(#2529) Deloitte is proceeding with FDS reviews for GCSN-S4 interaction, and yet we have no E2E architecture diagram for GCSN, and no involvement from GCSN IT (DXC). Deloitte is asking the GCSN team to review FDS documents for individual calls such as Order Simulate, Order Create etc. My recommendation is to first review an E2E architecture design for GCSN, so that all business SMEs can see the complete picture before diving into one specific piece of it. After all, besides SAP, GCSN interacts with many systems today such as Siebel, MDM, CVS, SNR, SABA etc. Many of those systems are getting retired, and most of the master data is changing. So before reviewing the details of an individual interface we need to understand the E2E architecture. Deloitte does not have such an E2E view, and they are proceeding to design the individual interfaces without it. We have S4 IT representation in those calls, but rarely any IT representation for GCSN – in fact we never have DXC in the calls. This does not bode well for all the GCSN development that needs to take place in the near future. When I ask why that is I am told that it is related to contractual negotiations with DXC which are still not finalized. ​ | Anderson, Rachel | 3/26/2018 | Open
RAID Snapshot:
April 6, 2018

## Slide 4: BA OM, Services, Finance, & Supply Chain (Scenario 4)
Key accomplishment
Boundary Apps deep dive and design enablement documentation completed for scenario 4 process steps
Completed validation session walk through of architectural diagram for scenario 4
Scenario 5 validation not completed as due to inadequate session length
Next Steps | Owner | ECD
ABM team to answer outstanding RAID log items in order to complete the architecture (#2582, 2583, 2585) | ABM team | 4/6
Post RAID closure, BA to update scenario spreadsheet as required | BA team | 4/6
Post RAID closure and BA updates, Global Architecture to update architecture views as required | GA Team | 4/6
Close open question regarding retirement of WWCLASS and managing spare parts - if WWCLASS GTS capability will be available in 2.4 | ABM team | 4/6
Confirm with master data team how iReturns get master data from legacy systems and from S4 | ABM team | 4/6
Confirm if Trax is sending feedback loop to S4 for Invoice Processing | ABM team | 4/6
RAID | Owner | ECD | Status
(#2585) Acknowledge back to EPS for each type of message in the original task steps (currently reflected as 12a, 15a, 17a, 18a). Acknowledge back to EPS for the message in the original task steps (currently reflected as 27a) | James Stein | 4/2 | Open
(#2582) Shipment Processing, Invoice processing, custom duties, return window calculation | Joe Salucci | 4/2 | Open
(#2583) WWCLASS process – there is a need to interact with the system of record for import/export classification data – this needs to be called in this process | Sahir Gaulkar | 4/2 | Open
RAID Snapshot:
April 6, 2018

## Slide 5: BA OM, Services, Finance, & Supply Chain (Scenario 5)
Key accomplishment
Validate Session completed for Field Service by HPE Technician - out of Warranty and no Service Contract (T&M)
Next Steps | Owner | ECD
Prashanth Anreddy to provide revised process steps by EOD 4/5 | ABM team | 4/6
Update architecture view based on feedback provided during session | BA team | 4/6
RAID | Owner | ECD | Status
(#2901)​ Update the steps to include quote communication step between Step 7 and Step 8 | Anreddy, Prashanth | 4/6/2018 | Open
(#2903) ​Create Shipment order and ship the parts Umakanth to work with Rosa and April to update the slide for the correct apps list | Potula, Umakanth | 4/6/2018 | Open
(#2906) ​Case closure/Workflow workflow and billing steps needs to be revised with Deloitte teams. | Anreddy, Prashanth | 4/6/2018 | Open
RAID Snapshot:
April 6, 2018

## Slide 6: BA OM, Services, Finance, & Supply Chain (Scenario 6)
Key accomplishment
Completed full validation session for Scenario 6 Boundary Applications
Conducted detailed walk through of architectural diagram
Continued to gather preliminary potential change topics for Scenario 6 regarding boundary applications
Next Steps | Owner | ECD
Close open RAID Items tagged to Scenario 0 prior to Align CRP | ABM Team | 4/6
Incorporate outcomes from the cross functional Scenario 6 Validate CRP | Luigi Scinicariello | 4/6
RAID | Owner | ECD | Status
(#2407) Return Product - Understanding process to dismantle returned product and discuss internal order options for dismantling product​(ABM CRP Scenario 6 - Returns with Credit)​​ | Kollu Bhatavachalam Prash | 4/10 | Open
(#2408) Provide product structure view for various ABM Scenarios (ABM CRP Scenario 6- Returns with Credit)​ | Steve Gajewski | 3/12 | Open
(#2545) Provide impact of ABM on the current usage of CTO Ids in sales and return orders​ | Suman Bhattacharya | 4/6 | Open
RAID Snapshot:
April 6, 2018

## Slide 7: BA OM, Services, Finance, & Supply Chain (Scenario 7)
Key accomplishment
Original scenario 7 for renewal is validated
Cancellations and amendments pending on CRP team
Next Steps | Owner | ECD
Update architecture based on upstream deep dives | BA Team | 
RAID | Owner | ECD | Status
(#2511) Open Item: Is the logic to identify opportunities in EAP or S4? Which one sends this data to SFDC Deep-dive session /Seek Approval from Architecture Team on the proposal to drive quote/opportunity creation by EAP.​​ | Soroka, Eugene A | 3/30 | Open
(#2461) Open Item: Will quote start in Hybris CPQ and be sent to S4, or start in S4? (Will opportunities from SFDC go to Hybris or S4?) Present Pros and Cons of Service Order/Quote creation options​ | Jagadp, Pandey | 3/23/2018 | Open
(#2328) Need detailed review of IB Next how it is aligned to NextGen IT project ​with relation to EAP requirements | Read, Kimberly (Enterprise Architect) | 4/6/2018 | Open
RAID Snapshot:
April 6, 2018

## Slide 8: BA OM, Services, Finance, & Supply Chain (Scenario 8)
Key accomplishment
Completed review of Boundary applications involved in planning, Aruba (Edge) and Hybrid IT product (IBP), and Spares (Servigistics)
Next Steps | Owner | ECD
Will log open items and make updates to architecture diagrams based on feedback received | BA team | 4/6
Update Architecture | BA | 4/6
RAID | Owner | ECD | Status
(#1650) Determine IBP-S4 Integration approach and the bridging strategy for IBP Integration. Existing non-ABM RAID | Balaraj Pudota | 4/16 | Open
(#2734) ​Planning BOM design (Hyrbid IT, Aruba) | Anand Srinivasan | 4/10 | Open
(#2735) Demand Planning forecast level changes | Anand Srinivasan | 4/10 | Open
(#2761) Can we aggregate demand planning for SC Aruba (Edge) products with Spares, instead of sending two separate signals to partners through Ariba? They are identical units and same contract manufacturers. | Steve Winterfeld, Steve | 4/16 | Open
RAID Snapshot:
April 6, 2018

## Slide 9: Boundary Applications/Global Architecture (Scenario 9)
Key accomplishment
Completed Validation for Hard Bundle for Hardware/Software with Services (Scenario 9) from a Boundary Applications standpoint
Reviewed architecture diagram and obtained feedback
Next Steps | Owner | ECD
Architecture views to be updated based on feedback obtained during the validate session | GA team | 
RAID | Owner | ECD | Status
(#2832) ​Scenario 9 - Send Aruba product from DC to CC. Step 65: Not paying freight bills through GP Ariba (Susan Ryan). Paid through Trax. Ariba cannot support logistics processes. Logistics approvals process in TRAX. Anna Pham/Gilles to work with Susan Ryan to determine the correct logistics payment process (Anna Pham) Step 64: Are all the freight payments moving through S/4 -> SWIFT? Need to engage on freight payment process. Currently paying governments taxes/duties through variety of indirect procurement processes. (Anna Pham) | Pham, Anna |  | Open
(#2834) Scenario 9 - Billing and Invoicing Step 101 - Aruba category determination. Sales order attribute which is rev rec relevant. Connect with Brett Nelson to explain. Alberto Vargas - internal process, relevant for billing or processing and should not be Aruba specific. (Hitesh Tewari) | Tewari, Hitesh |  | Open
(#2836) ​Scenario 9- Billing and Invoice Step 103 - cannot do GTS validation check after the shipment has been released. Once released to the carrier the equipment isn't stopping. The goods must be clean and approved before release to logistics. Require 1 final GTS screening after shipment within 24 hours. Susan Ryan, Jospeh Petronis, Brett Nelson, Guillermo Vasquez | Periasamy, Prabhu M |  | Open
(#2838) ​Scenario 9 - Revenue Recog Profit center determination should be done during time of sales order creation. Field on the sales document, should be determined during the sales document creation | Tewari, Hitesh |  | Open
​​(#1759) Decision needed on a bridging solution for 1) SNR and 2) SWOP | Murray, Iain (SEO) |  | Open
(#2442)"​Understand processs for regulatory check for shipments ​​​ " | Chavan, Rohit |  | Open
RAID Snapshot:
April 6, 2018

## Slide 10: Boundary Applications/Global Architecture (Scenario 10)
Key accomplishment
Validate Session completed for Service-led Subscription, custom SOW or Consumption Service Sales
Next Steps | Owner | ECD
Update architecture view based on feedback provided during session | BA team | 
RAID | Owner | ECD | Status
No RAID were raised |  |  | 
RAID Snapshot:
April 6, 2018